1. Phase 0 – Research & Environment Setup (4 tuần)

1.1 Research

- 1.1.1 Qt + OpenGL rendering pipeline

- 1.1.2 OpenCV (feature detection: SIFT/ORB)

- 1.1.3 SfM pipeline (Structure from Motion)

- 1.1.4 PCL basics

- 1.1.5 ONNX Runtime / TensorRT

1.2 Environment Setup

- 1.2.1 CMake configuration

- 1.2.2 Build OpenCV

- 1.2.3 Build PCL (rủi ro cao)

- 1.2.4 Integrate Qt + OpenGL

- 1.2.5 Setup ONNX Runtime

1.3 Technical Risk Handling

- 1.3.1 Debug build errors (PCL, VTK, OpenCV)

- 1.3.2 DLL conflicts

- 1.3.3 Memory issues

1.4 Output

- Build OK toàn bộ hệ thống.

2. Phase 1 – 3D Viewer (5 tuần)

2.1 UI + Rendering

- 2.1.1 Load ảnh (PNG/JPG)

- 2.1.2 Load model OBJ

- 2.1.3 OpenGL rendering

2.2 Interaction

- 2.2.1 Zoom

- 2.2.2 Rotate

- 2.2.3 Pan

2.3 Testing

- 2.3.1 UI test

- 2.3.2 Render correctness

- 2.3.3 Performance basic

2.4 Risk Handling

- Black screen (OpenGL)

- Coordinate system mismatch

2.5 Output

- Viewer hoàn chỉnh

3. Phase 2 – 3D Reconstruction (8 tuần)

3.1 Algorithm Research (2 tuần)

- 3.1.1 Feature detection (SIFT/ORB)

- 3.1.2 Matching (FLANN / BFMatcher)

- 3.1.3 Epipolar geometry

- 3.1.4 Triangulation

3.2 Implementation

3.2.1 Feature Detection

- detect keypoints

- descriptor extraction

3.2.2 Feature Matching

- match filtering

- RANSAC

3.2.3 Camera Pose

- Essential matrix

- recoverPose

3.2.4 Triangulation

- generate point cloud

3.3 Integration

- Show point cloud in viewer

3.4 Testing

- Accuracy test

- Noise analysis

3.5 Risk Handling

- Matching sai

- Reconstruction lỗi

- Scale ambiguity

3.6 Output

- Basic 3D reconstruction

4. Phase 3 – 3D Processing (4 tuần)

4.1 PCL Integration

- 4.1.1 Link PCL vào project

- 4.1.2 Convert data (OpenCV → PCL)

4.2 Processing Algorithms

- 4.2.1 Noise filtering

- 4.2.2 Downsampling (VoxelGrid)

- 4.2.3 Outlier removal

4.3 Testing

- Compare before/after

4.4 Risk

- Heap corruption

- Memory alignment

4.5 Output

- Clean point cloud

5. Phase 4 – AI Integration (7 tuần)

5.1 Research (2 tuần)

- 5.1.1 ONNX Runtime

- 5.1.2 Model segmentation/detection

- 5.1.3 Input preprocessing

5.2 Integration

- Load model ONNX

- Inference pipeline

5.3 Apply AI

- Filter ảnh đầu vào

- Improve matching

5.4 Testing

- Accuracy improvement

- Performance

5.5 Risk

- Model không chạy

- GPU/CPU mismatch

- Latency cao

5.6 Output

- AI-assisted reconstruction

6. Phase 5 – Optimization & Refactor (4 tuần)

6.1 Performance

- Multithreading (QtConcurrent / std::thread)

6.2 Refactor

- UI / Core / AI separation

6.3 Code Quality

- Smart pointers

- Memory leak check

6.4 Testing

- Unit test core modules

6.5 Output

- Production-ready structure

7. Buffer & Risk Handling (4 tuần)

- Fix bug lớn

- Rework algorithm

- Performance tuning